## Sheet1
Phases | Start Date | Days to Complete
Project Planning | 2024-07-03 | 1
Research and Analysis | 2024-07-04 | 7
User Interface (UI) Design | 2024-07-11 | 7
Study on API’s to understand which details are provided | 2024-07-18 | 7
Frontend Development | 2024-07-25 | 15
Backend Development | 2024-08-09 | 15
Testing | 2024-08-24 | 5
Deployment | 2024-08-30 | 2
Training and Documentation | 2024-09-01 | 5
Post-Implementation Review | 2024-09-06 | 5
Project Closure | 2024-09-11 | 1